## Slide 1: Biennial Performance Audit of the Department of TRANSPORTATION
Josh PascH, CPA
City Auditor
August 2, 2023 at 9:00 Am – BOARD of Estimates Meeting

## Slide 2: OUTLINE
Audit Objectives and Scope
Finding
Implementation Status of Prior Findings
Questions?

## Slide 3: Audit Objectives, Scope, and Methodology
Determine whether the DOT's Federal Project Closeout process is efficient and effective
Follow-up on prior findings and recommendations included in the previous Biennial Performance Audit Report
Scope – Fiscal Years 2021 and 2020
Affected divisions are Contract Administration, DOT Fiscal and the TEC (Transportation Engineering and Construction) Division

## Slide 4: Audit Methodologies
Researched the State Highway Administration (SHA) Manual for Construction on federally funded road construction projects as well as Maryland laws and literature concerning the rules noted in the SHA Manual
Interviewed key individuals from DOT and Bureau of Accounting and Payroll Services to obtain an understanding of the policies and procedures and systems that govern the Closeout Process for federally funded road construction projects
Identified the related risks and key controls regarding Federal Contract Closeout; then judgmentally selected samples and tested key controls

## Slide 5: Finding
Inefficiencies in the DOT Close Out Process Resulted in Delayed Revenues to the City.
Condition - DOT does not effectively monitor to make certain projects are closeout within reasonable timeframe.
  Out of 18 samples that we reviewed,
    Seven samples, or approximately 39 percent - DOT was not able to provide documentation
  Of the remaining 11 samples,
    Delays ranging from 16 months to 235 months (approximately 19.6 years)

## Slide 6: Finding (Continued…)
Summary of Time Spent to Complete Key Tasks that Affect Project Closeouts |  |  | 
Key Tasks | Minimum Months | Maximum Months | Number of Exceptions
Final Acceptance Date to Retainage Release Date 1 | 16 | 120 | 7
Final Acceptance Date to DOT Director's Signed-off Date on Certification of Work Completion2 | 8 | 173 | 8
DOT Director's Signed-off Date to The Date when Contract Administration (CA) Sent Final Package to DOT Fiscal2 | 6 | 32 | 5
The Date when CA Sent Final Package to DOT Fiscal to The Date when DOT Fiscal Sent Final Voucher to SHA3 | 9 | 74 | 8
Final Acceptance Date to The Date when DOT Fiscal Sent Final Voucher to SHA | 16 | 235 | 10
Notes: 1. Benchmark set at twelve months. 2. Benchmark set at three months. 3. Benchmark set at six months. |  |  | 

## Slide 7: Finding (Continued…)
Effect - Revenues (payments from the SHA to the City of Baltimore) become delayed.
Causes – The significant delays are because DOT:
Does not have established timeframes to complete one key task to the other
Does not task a division such as Contract Administration to track and monitor key tasks to be completed within the established time frame

## Slide 8: Finding (Continued…)
Recommendation - We recommend the Director of DOT establish policies and procedures to:
Establish timeframes to complete one key task to another
Grant authority to Contract Administration to track and monitor key tasks are completed within the established timeframes
Maintain documentation to track and monitor the key dates.

## Slide 9: Implementation Status of Prior Findings
No. of Findings | SERVICE | PERFORMANCE MEASURE | IMPLEMENTATION STATUS
2 | 683 - Street Management | % of potholes repaired within 48 hours of reporting | Implemented
1 | 683 - Street Management | Cost of Lane Per Mile Resurfaced by Internal Crews | Implemented
1 | 693 - Parking Enforcement | # of Citations issued | Implemented

## Slide 10: Questions?
Subtitle goes Here